


APPENDIX 4


Test Procedure for the Product


TABLE OF CONTENTS	


Testing of the product	1
1.1	No-Load Function Test	2
1.2	Trial Run with Load	3
1.3	Acceptance Test	4




[bookmark: _Toc180700765][bookmark: _Toc159340460]
Testing of the productTo be proposed by supplier as part of the RFP response


[bookmark: _Toc159340461][bookmark: _Toc180700766]No-Load Function Test
When all erection, installation, assembly etc. of the Product have been completed at the Site [ADD IF APPLICABLE: and the Product has been incorporated into the works of which the Product shall constitute a part at the Site], the No-Load Function Test shall be carried out on the Product at the Site, comprising inspections and tests, such as checks of the completion of mechanical and electrical equipment, functional tests of all drives, switches and all control systems, checking of safety devices, verifying the [INSERT OTHER RELEVANT PROPERTIES OF THE PRODUCT THAT SHALL BE CHECKED].

The Buyer is responsible for the No-Load Function Test. The test shall be carried out by the Buyer and the Seller shall attend the test.

If the test results demonstrate that the Product are in conformity with Appendix 3 (Technical Specifications), Appendix 5 (Scope of Supply) [COMMENT: INSERT REFERENCES TO THE APPENDICES WHERE THE PROPERTIES THAT SHALL BE TESTED IN THE NO-LOAD FUNCTION TEST ARE LISTED OR DESCRIBED], the No-Load Function Test shall be considered satisfactorily completed. Otherwise the Seller shall promptly make the corrections and adjustments necessary to bring the Product in conformity with the said specifications and thereafter new No-Load Function tests shall be carried out until the test is satisfactorily completed.

After satisfactorily completion of the No-Load Function Test, the Seller shall prepare a test report in duplicate, which shall be confirmed and signed by the representatives of both Parties.

The report will be signed, even if there are some minor defects that have not been remedied, but which will not affect any of the tests that will follow or the future operation of the Product. Such defects shall be noted in the report and the Seller shall remedy all such defects without delay.
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Trial Run with Load
The Trial Run With Load shall be carried out after satisfactorily completion of the No-Load Function Test and after completed CE-marking of the works of which the Product shall constitute a part at the Site. The Trial Run With Load shall demonstrate that the Product is properly designed [COMMENT: ADD IF THE SELLER ACCORDING TO THE CONTRACT IS RESPONSIBLE FOR SUPERVISING OF AND PROVIDING INSTRUCTIONS FOR THE ERECTION WORK: and erected] to achieve the capacity warranted in the performance warranty, Appendix 1.

The raw material intended for the use of the Product shall be used for the Trial Run With Load.

The Buyer is responsible for the Trial Run With Load. The test shall be carried out by the Buyer and the Seller shall attend the test.

The Trial Run With Load shall be carried out under a period of [INSERT A PERIOD OF TIME WHICH IS LONG ENOUGH TO ESTABLISH WITH CERTAINTY THAT THE PRODUCT HAS THE CAPACITY IN THE PERFORMANCE WARRANTY]. During the Trial Run With Load the Product shall be run with increasing load up the capacity warranted in the performance warranty, Appendix 1, or, if the Buyer cannot provide the sufficient amount of load, up to the maximum capacity that can be tested. Final adjustments shall be made under load conditions. 

[DETAILED SPECIFICATION OF WHICH TESTS TO BE CARRIED OUT WILL BE COMPLETED TOGETHER WITH THE SELLER BEFORE SIGNING OF THE CONTRACT]

If the capacity warranted in the performance warranty, Appendix 1, or the maximum capacity that can be tested in accordance with the above, is not achieved, the Seller shall promptly make the necessary corrections and adjustments with regard to malfunctions of the Product and thereafter new Trial Runs With Load shall be carried out until the warranted capacity is achieved.

When the Product achieves the capacity warranted in the performance warranty, Appendix 1, or the maximum capacity that can be tested in accordance with the above, and in all other respects are ready for the Acceptance Test, the Trial Run With Load shall be considered satisfactorily completed.

After satisfactorily completion of the Trial Run With Load, the Seller shall prepare a test report in duplicate which shall be confirmed and signed by the representatives of both Parties, correctly confirming that the Product is ready for the Acceptance Test.

The report will be signed, even if there are some minor defects that have not been remedied, but which will not affect any of the tests that will follow or the future operation of the Product. Such defects shall be noted in the report and the Seller shall remedy all such defects without delay.
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Acceptance Test
After the Trial Run With Load the Buyer shall carry out the Acceptance Test of the performance of the Product in combination with the [INSERT THE NAMES OF THE PARTS THAT SHALL BE TESTED TOGETHER WITH THE PRODUCT (THAT IS, PARTS THAT THE PRODUCT DEPEND ON AND WHICH ARE DEPENDING ON THE PRODUCT], and all other equipment being part of the [INSERT THE NAME OF THE PART OF THE PROJECT, E.G. personnel shaft or conveyor system]  (the “[INSERT SAME NAME AS CAPITALIZED TERM, E.G. Personnel Shaft or Conveyor System]”). 

[The Delivery Test shall not be commenced before the Product has been approved by an independent third party inspector in accordance with [INSERT RELEVANT STANDARDS/REGULATIONS FOR THE BUSINESS THAT THE PRODUCT RELATE TO]. Said inspection shall be ordered, co-ordinated and paid for by the [Seller/Buyer]. The Buyer shall be entitled to appoint the company that shall carry out the inspection.] [COMMENT: APPLICABLE IF A THIRD PARTY INSPECTION IS REQUIRED]
 
The Acceptance Test shall take place to establish whether the Product together with the other parts of the [INSERT THE NAME OF THE PART OF THE PROJECT AS CAPITALIZED TERM, E.G. Personnel Shaft or Conveyor System] fulfil the performance warranty, Appendix 1 and in all other respects are in conformity with the Contract and available for normal operations at the Site.

[DETAILED SPECIFICATION OF WHICH TESTS TO BE CARRIED OUT WILL BE COMPLETED TOGETHER WITH THE SELLER BEFORE SIGNING OF THE CONTRACT]

Responsibilities
The Buyer is responsible for the Acceptance Test. The test shall be carried out by the Buyer and the Seller shall attend the test.

Carrying out the test
The Buyer’s operating personnel under the Seller’s supervision and advice shall carry out the Acceptance Test. During the Acceptance Test, the Buyer’s personnel shall conduct the operation and maintenance of the Product in accordance with the Seller’s written reasonable instructions provided by Seller to Buyer prior to the Acceptance Test.

The Seller shall make spare parts and wear parts that may be required during the Acceptance Test available to the Buyer from the Seller’s stock. During the test period, spare parts and wear parts shall be at direct and immediate availability to Buyer. 

During the Acceptance Test, the Product shall be operated under full load conditions during a period of [INSERT A PERIOD OF TIME WHICH IS LONG ENOUGH TO ESTABLISH WITH CERTAINTY THAT THE PRODUCT HAS THE CAPACITY IN THE PERFORMANCE WARRANTY AND IN ALL OTHER RESPECTS ARE IN CONFORMITY WITH THE CONTRACT AND AVAILABLE FOR NORMAL OPERATIONS AT THE SITE] at [INSERT APPROPRIATE NUMBER OF OCCASSIONS] different occasions with [INSERT APPROPRIATE PERIOD OF TIME BETWEEN THESE OCCASIONS] in between the tests.

Should the weather conditions prior to and during the Acceptance Test prevent proper execution of the test according to the representatives of both Parties, the Acceptance Test shall be postponed until the weather conditions are suitable.

Remediation of defects
If the Acceptance Test shows that the Product does not fulfil the performance warranty, Appendix 1, or otherwise is not in conformity with the Contract or available for normal operations at the Site, the Seller shall take the necessary measures for the Product to achieve the warranted performance, bring the Product in conformity with the Contract and available for normal operations at the Site within the shortest possible time. Thereafter new Acceptance Tests shall be carried out until the test is satisfactorily completed.

Completion of the test
The Acceptance Test shall be considered satisfactorily completed when the test demonstrates that the Product fulfil the performance warranty, Appendix 1, during a continuous period of [INSERT A PERIOD OF TIME WHICH IS LONG ENOUGH TO ESTABLISH WITH CERTAINTY THAT THE PRODUCT HAS THE CAPACITY IN THE PERFORMANCE WARRANTY AND IN ALL OTHER RESPECTS ARE IN CONFORMITY WITH THE CONTRACT AND AVAILABLE FOR NORMAL OPERATIONS AT THE SITE] at [INSERT APPROPRIATE NUMBER OF OCCASSIONS] different occasions with [INSERT APPROPRIATE PERIOD OF TIME BETWEEN THESE OCCASSIONS] in between the tests and in all other respects are in conformity with the Contract and available for normal operations at the Site.

Report
When the Acceptance Test has been satisfactorily completed, the Seller and the Buyer shall sign a test report in the format as attached to this Appendix 6, which shall be considered a correct and complete record of the Acceptance Test. [COMMENT: TEST REPORT FORMAT TO BE PROVIDED BY SELLER AND APPROVED BY BUYER PRIOR TO SIGNING OF THE CONTRACT]
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