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APPENDIX 6 



DOCUMENTATION
FOR THE SUPPLY OF
FILTER BELT EQUIPMENT
 
FOR

Quinto Plasterboard Plant,
Spain





CONTRACT REFERENCE: 

10190-C50-TSP-GMT-001 Rev A









	
	Item
	Documents
	Quantity
	Latest Date
	Language
	Hasler’comments

	1
	Plant Marking.  In addition to the equipment manufacturer's standard nameplate; a name plate shall be permanently attached to each all equipment/skids bearing the following information:
Equipment Title / Equipment Item Number 
Skid Supplier’s name and contact details.
Plant reference number 
Saint-Gobain Project number (10190)
	One per skid/tank. Physical tag

	

With Equipment Delivery
	English (1 Copy), Spanish (1 Copy)
	- One plate for the filter, one for the motor unit, one for the vacuum pump, one for the separator tank and one per CE equipment purchased from a supplier.

-  From January 2026, depending on developments in the Machinery Directive, paper versions will no longer be mandatory; only digital versions will be required. If paper versions are required, a substantial budget must be allocated given the volume and time involved.

- Documents only in English

	2
	Project Programme (Item 4 on Appendix 4)
	One per month of project

	30 days from PO raised 
	English
	

	3
	All valves and in-line equipment shall be provided with suitable equipment number tags attached to the equipment
Tag number to be agreed between parties after equipment design.
	Physical tag
	With Equipment Delivery
	_
	Sant Gobain  provides TAG numbers such as RS0540 (Gelsa’s Filter) , which will be used in PID, PFD and other documents.

	4
	Preliminary Loading, Power Consumption and Utility Requirement Information. 
	Electronic copy
	30 days from PO raised
	English
	6 weeks after PID/PFD validation 

	5
	Certified Loading Information.
	Electronic Copy
	60 days from PO raised
	English
	

	6
	Final Power Consumption and Utility Requirement Information.
	Electronic Copy
	60 days from PO raised
	English
	

	7
	Layout and Dimensional information. To be provided as Inventor-compatible 3D models, in addition to 2D layout drawings.
	Electronic copy
	30 days from PO raised
	English
	

	6
	Engineering Line Diagram (ELD), Equipment Lists and IO lists. 
	Electronic copy
	30 days from PO raised
	English
	PFD/PID supplied  after 8 weeks from Purchase Order (PO)

	7
	Manufacturing Drawings for Approval

Bought-out parts / equipment data sheet and necessary documentation for Approval
	Electronic copy
	60 days from PO raised
	English/ Spanish
	Manufacturing Drawings not provided, only General Assembly (GA)like Gelsa filter.
GA : 8 weeks after PO

	8
	Spare Parts List- Including highlighted equipment as per Appendix 1 Specification.
	Electronic copy
	60 days from PO raised
	English/ Spanish
	6-8 weeks after GA and PFD/PID validation

	9
	Installation, Commissioning & Operation Supporting documentation:

· Lubrication schedules where applicable
· Equipment commissioning check sheets
· Finalised motor, gearbox and instrument lists
· Operation, Installation and Maintenance manuals for each machine
· Equipment certification, whichever is relevant to the country of installation
	Electronic copy
1 paper copy
	



At Factory Acceptance Test
	English/ Spanish
	

IOM, filter notice in English and Spanish.
Supplier notice : English only

	10
	
‘As-Built’ documents and drawings:

· Finalised ‘As Built’ drawings and 3D Models
· Finalised Equipment Summary List (with confirmed item references, sizes and materials of construction, as chosen by the Supplier and approved by the Purchaser)
· List of Equipment, Fixings and Consumables being delivered to site
· Description of any special/specific installation or assembly methods required in the erection / installation
· Tests, material and welder’s certificates
· Vessel and pipe work materials certification (tightness test, pressure test… - see Appendix 1)

	Electronic copy
1 paper copy
	









With Equipment Delivery
	English/ Spanish
	Electronioc copy : okay
Paper copy : deviated

	11
	Final Tests and Inspection Reports for all Equipment
	Electronic copy
2 paper copies
	10 days before takeover
	English/ Spanish
	Paper copy : deviated

	12
	CE Marking Documentation (including Declaration)
	Electronic Copy and Paper Copy
	10 days before takeover
	English/ Spanish
	Paper copy : deviated

	13
	Shipping Documents as required for Importation
	Electronic Copy
	7 days before shipping
	English/ Spanish
	

	14
	Delivery Documentation Accompanying the Transportation of the Equipment
	Electronic Copy
	7 days before shipping
	English/ Spanish
	


The Supplier must send all documents and documentation requested by the Purchaser as specified below and following the Appendix 4 Time Schedule.

NOTES:

· All 2D drawings should be fully compatible and editable by the Purchaser and/or AutoCAD (version to be confirmed before Order)
· All documentation should be supplied in English (mandatory). All documents should be fully compatible and editable by the Purchaser.
· Documents format : PDF, DWG, Excel, Word
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