	
APPENDIX 4

TIME SCHEDULE





Dates for fulfilment of operations under the Agreement and any giving of necessary documents are set as follows:

	Nr
	Operations milestones for Contractor
	Milestone Date 
(dd-mm-yyyy)

	1
	Contract Effective Date
	20-02-2026

	2
	Delivery of Drawings for manufacturing- for Purchaser Approval
	See (1)

	3
	Delivery of Technical Documentation (Data Sheets etc.) for externally sourced equipment and components- for Purchaser approval (Appendix 6 item 2)
	See (2)

	4
	Layout & Dimensional information including 3D models. 
	20-03-2026

	5
	Delivery of Initial Project Programme
	20-03-2026

	6
	Preliminary Loading, Power Consumption & Utility Requirement Information
	20-03-2026

	7
	Delivery of Manufacturing documentation for review (Appendix 6 item 4)
	20-03-2026

	8
	Approval of Project Programme and Manufacturing Documentation by Purchaser
	27-03-2026

	9
	Certified Loading, Power Consumption & Utility Requirement Information
	30-04-2026

	10
	Factory Acceptance Test (F.A.T.) of the Equipment at Contractor’s site
	27-02-2027

	11
	Signature of Factory Acceptance Certificate
	07-03-2027

	12
	Delivery of shipping documentation prior to shipping (Appendix 6 item 11)
	07-03-2027

	13
	Equipment ready for transport from Contractor’s workshop
	15-03-2027

	14
	Delivery of As-Build Documentation (Appendix 6 item 8 and 9)
	15-03-2027

	15
	Shipping of the Equipment, Road Transport
	17-03-2027

	16
	Delivery date of shipping documentation after shipping (Appendix 6 item 11)
	21-03-2027

	17
	Delivery Date of the Equipment to Site
	25-03-2027

	18
	Take-Over
	30-05-2027

	19
	Performance Test period
	Period of 180 days from Take-Over

	20
	Date of Acceptance
	26/11/2027 (180 days after Take-Over)

	21
	Signature of Acceptance Certificate
	30/11/2027




(1): The Drawings for manufacturing must be sent by the Contractor to the Purchaser for approval before beginning to manufacture the equipment. If not, the Purchaser can refuse the equipment.

(2): The Contractor shall send all necessary Documents detailing the externally sourced Equipment (Data sheets etc.) to the Purchaser for approval before ordering any Equipment. The Contractor is not authorised to buy Equipment prior to Purchaser Approval. 



