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APPENDIX 6 



DOCUMENTATION
FOR THE SUPPLY OF
FILTER BELT EQUIPMENT
 
FOR

Quinto Plasterboard Plant,
Spain





CONTRACT REFERENCE: 

10190-C50-TSP-GMT-001 Rev A









	
The Supplier must send all documents and documentation requested by the Purchaser as specified below and following the Appendix 4 Time Schedule.
	Item
	Documents
	Quantity
	Latest Date
	Language

	1
	Plant Marking.  In addition to the equipment manufacturer's standard nameplate; a name plate shall be permanently attached to each all equipment/skids bearing the following information:
Equipment Title / Equipment Item Number 
Skid Supplier’s name and contact details.
Plant reference number 
Saint-Gobain Project number (10190)
	One per skid/tank. Physical tag

	

With Equipment Delivery
	English (1 Copy), Spanish (1 Copy)

	2
	Project Programme (Item 4 on Appendix 4)
	One per month of project

	30 days from PO raised 
	English

	3
	All valves and in-line equipment shall be provided with suitable equipment number tags attached to the equipment
Tag number to be agreed between parties after equipment design.
	Physical tag
	With Equipment Delivery
	_

	4
	Preliminary Loading, Power Consumption and Utility Requirement Information. 
	Electronic copy
	30 days from PO raised
	English

	5
	Certified Loading Information.
	Electronic Copy
	60 days from PO raised
	English

	6
	Final Power Consumption and Utility Requirement Information.
	Electronic Copy
	60 days from PO raised
	English

	7
	Layout and Dimensional information. To be provided as Inventor-compatible 3D models, in addition to 2D layout drawings.
	Electronic copy
	30 days from PO raised
	English

	6
	Engineering Line Diagram (ELD), Equipment Lists and IO lists. 
	Electronic copy
	30 days from PO raised
	English

	7
	Manufacturing Drawings for Approval

Bought-out parts / equipment data sheet and necessary documentation for Approval
	Electronic copy
	60 days from PO raised
	English/ Spanish

	8
	Spare Parts List- Including highlighted equipment as per Appendix 1 Specification.
	Electronic copy
	60 days from PO raised
	English/ Spanish

	9
	Installation, Commissioning & Operation Supporting documentation:

· Lubrication schedules where applicable
· Equipment commissioning check sheets
· Finalised motor, gearbox and instrument lists
· Operation, Installation and Maintenance manuals for each machine
· Equipment certification, whichever is relevant to the country of installation
	Electronic copy
1 paper copy
	



At Factory Acceptance Test
	English/ Spanish

	10
	
‘As-Built’ documents and drawings:

· Finalised ‘As Built’ drawings and 3D Models
· Finalised Equipment Summary List (with confirmed item references, sizes and materials of construction, as chosen by the Supplier and approved by the Purchaser)
· List of Equipment, Fixings and Consumables being delivered to site
· Description of any special/specific installation or assembly methods required in the erection / installation
· Tests, material and welder’s certificates
· Vessel and pipe work materials certification (tightness test, pressure test… - see Appendix 1)

	Electronic copy
1 paper copy
	









With Equipment Delivery
	English/ Spanish

	11
	Final Tests and Inspection Reports for all Equipment
	Electronic copy
2 paper copies
	10 days before takeover
	English/ Spanish

	12
	CE Marking Documentation (including Declaration)
	Electronic Copy and Paper Copy
	10 days before takeover
	English/ Spanish

	13
	Shipping Documents as required for Importation
	Electronic Copy
	7 days before shipping
	English/ Spanish

	14
	Delivery Documentation Accompanying the Transportation of the Equipment
	Electronic Copy
	7 days before shipping
	English/ Spanish



NOTES:

· All 2D drawings should be fully compatible and editable by the Purchaser and/or AutoCAD (version to be confirmed before Order)
· All documentation should be supplied in English (mandatory). All documents should be fully compatible and editable by the Purchaser.
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